## Slide 1: Theory-based approaches for evaluative programme monitoring: lessons from Iraq
Peacebuilding M&E Solutions Forum
Jesse McConnell
Nautilus Consulting
jesse@nautilusconsulting.org

## Slide 2: Outline
Introduction
  Context: Conflict, Stability and Security Fund (CSSF) in Iraq
Complex policy programme theory
  Systemic problems & indirect impact
Embracing complexity: the CSSF – Iraq programme
  Complexity characteristics
Theory-based attribution
  Methods & theory
Application: theory-based programme monitoring
  Categorical indicators, adoption, and implementation
Lessons Learned
Conclusion

## Slide 3: 1. Introduction
Conflict, Stability and Security Fund
  The UK’s Conflict, Security and Stability Fund (CSSF) is a cross-government fund supported primarily by the Foreign and Commonwealth Office (FCO), the Department for International Development (DFID), and the Ministry of Defense (MoD)
  It has an annual budget of approximately £1.3 billion (primarily for Overseas Development Assistance), mandated to deliver programming that responds to challenging environments, such as protracted conflict or political crises, and in support of the UK’s National Security Council’s strategic objectives
  Presentation of supported M&E system development & implementation for the CSSF in Iraq during 2015-2017
  Programme objectives: to support a more stable, secure, and unified Iraq

## Slide 4: 2. Complex policy programme theory
Complex policy programmes:
  Approach to supporting lasting change sensitive to the complex and systemic nature of major challenges (e.g. poverty, conflict, climate changing)
  Based on recognition that these ‘major challenges’ are constituted by institutions and complex systems of intermediary agents, such as organisations, governments, and institutions, which govern behaviour and the way that societies interact – not isolated or localised
  Design logic: if the structural policies of a particular system can be changed to a desired end, the system itself can be changed = greater impact on the population within the system’s aegis than an isolated or singular intervention

## Slide 5: 2. Complex policy programme theory
Complex policy programmes:
  An indirect impact intervention: support to an intermediary (agent, organization, department or firm) with the ability to affect change within a system
  Indirect nature of impact -> based on inherent premise of an ability to influence both the intermediaries and the wider system to take up its supported changes
    Premise: influence plays a fundamental role in effective policy interventions’ ability to achieve their intended change
  Often overlooked, but if more explicit, can provide a clearer foundation from which to develop the intervention’s change pathways along a process of influencing the intermediary agent directly and the wider system indirectly

## Slide 6: 2. Complex policy programme theory
Source: adapted from Montague, Young and Montague (2003)
Notes:   Can be described as an intervention’s reach and the levels of influence it may have as ‘spheres of influence’:
  - Outputs = sphere of direct control
    Outcomes & impact = spheres of influence (direct and indirect)
  By incorporating this influence dimension into the structure of a intervention’s design elements (theory of change, results framework, etc), it assists an intervention in more effectively and holistically monitoring its ability to achieve results.

## Slide 7: 3. Embracing complexity: the CSSF in Iraq
The CSSF in Iraq was a largely complex policy programme:
  Objectives included…
    Influence shifts in the broader governance systems;
    Support the immediate stabilisation for newly liberated areas and returnees;
    Support a viable political settlement;
    Strengthen governance through more inclusive and effective institutions; and
    Support the security sector to provide more effective security to Iraqi citizens.
  Structure:
    Built around three or four strands (depending on the year):
      Strategic Communications
      Governance / Stabilisation
      Reconcilation / Reform
      Security & Justice

## Slide 8: 3. Embracing complexity: the CSSF in Iraq
  Complexity characteristics:
  Nonlinear (e.g. highly politicised environment)
  Emergent (outcomes emerge rather than defined ex ante)
  Coevolution (programme support interacts closely with intermediaries)
  Systemic (interdependence and inter-relational characteristics of component parts)
  Implications for monitoring:
  Sensitivity to systemic complexities of programme & delivery environment
  Conventional approaches based on linearity and certainty inadequate for nonlinearity and emergence
  Need flexibility to respond to evolving context and programming
  Ability to enable programme adaptation to context and political imperatives

## Slide 9: 4. Theory-based attribution
  Evaluator’s confounding question:
  How to credibly attribute an observed change to a particular intervention’s support.
    Particularly for complex programmes in challenging delivery environments
  Theory-based approaches to evaluation have gained prominence in recent years largely out of an increased sensitivity to complexity and an acknowledged need for more systemic change to underpin peace and development efforts

## Slide 10: 4. Theory-based attribution
  Inferring causality
  Approaches tend to trace the causal processes articulated in a theory of change
  ‘Process tracing’
    Particularly well-suited to studying complex programme environments and can capture emergent processes because it traces events over time, and it permits the study of complex causal relationships and provides a strong basis for inferring cause
    If it is possible to demonstrate the steps involved in an intervention’s progression from inputs to outcomes, then causal attribution is possible (Weiss, 1997)
    Contribution: important to consider other contributing factors along causal process (Mayne, 2012)
    Strong contextual understanding can then further strengthen the view towards other possible influencing factors on an intervention’s effects (Pawson, 2001)

## Slide 11: 4. Theory-based attribution
  Enables evaluative monitoring
  ‘Evaluative’ thinking:
    A combination of critical thinking, creative thinking, inferential thinking, and practical thinking (Patton, 2018, NDE) – particularly around how an intervention moves towards achieving its objectives
  By designing a monitoring that reflects the programme design logic – influence, uptake of support by intermediaries into broader system – provides a basis for process tracing
  Monitoring activities take on more critical reflection about the ongoing effectiveness of the programme processes
  Tracing progress towards outcomes
  Embeds evaluative thinking into routine monitoring

## Slide 12: 5. Application: theory-based monitoring

## Slide 13: 5. Application: theory-based monitoring

## Slide 14: 5. Application: theory-based monitoring
  Evaluative indicators for conflict sensitivity
  Based on conflict analysis to identify conflict drivers
  Develop indicators around conflict drivers to monitor conflict context
  Frames programme intermediate outcomes and outcomes, ensuring results target reducing the effect of conflict drivers (positive side of doing no harm)

## Slide 15: 5. Application: theory-based monitoring
  Categorical output indicators
  Output categories aim to capture broad range of support areas (rather than specific output details)
  Flexibility of indicator categories allows for the operational space needed for the adaptive nature of the programme while still reflecting its results

## Slide 16: 5. Application: theory-based monitoring
  Intermediate outcomes: adoption
  First step outside the programme’s direct sphere of control (outputs) and its reliance on influence (sphere of direct influence)
  Worded as the adoption of programme-supported outputs
  Reflects indirect impact design logic: intermediary assumed to take-up (adopt) the programme’s support (outputs)

## Slide 17: 5. Application: theory-based monitoring
  Outcomes: implementation
  Next step into the programme’s sphere of indirect influence to achieve its intended results
  Understood as the effective implementation of programme-supported outputs

## Slide 18: 5. Application: theory-based monitoring
  Impact: effects of output implementation
  Culmination of the programme’s effects
  Determined as the results of effectively implemented programme outputs.
  Worded as: a more secure and stable Iraq

## Slide 19: 6. Lessons Learned
  Nonlinearity & influence:
  Nonlinear causality (highly politicised context & conflict) mitigated by constant engagement from implementing partners with intermediaries
    Monitored through flexible categorical approach to indicators
    Emergence managed by monitoring broader logic of adoption and implementation (rather than specific outcomes)
Demand versus solution:
  Embedded nature of much of the support (e.g. TA in gov departments; community-driven reconciliation) responsive to the evolving environment and community needs
    Stakeholders involved in identifying problems and solutions
    Places indirect impact design feature as central implementation component – enhances uptake

## Slide 20: 6. Lessons Learned
  Flexibility & uncertainty:
  RF structure – categorical indicators, adoption and implementation levels – allow for uncertainty while capturing results
    Challenges: subjective aspect of defining categorical alignment for outputs
    Challenges: donor appetite for embedding flexibility into results framework unpredictable, particularly milestone and target setting
Causal inference:
  Embedding the ToC process into the RF structure it allows the programme to monitor causal processes and infer outcome- and impact-level results through observing success in these processes
    Evaluative benefits salient to challenging environments in which attribution is difficult to determine, or where the programme’s remit makes comprehensive evaluation methodologies prohibitive and resource-intensive

## Slide 21: 6. Conclusion
  Complex policy programmes present opportunities for enhanced and systemic impact, but present challenges to monitoring results and effectiveness
  A theory-based approach can provide greater flexibility in the mechanics of a monitoring framework that also enables a programme to overcome many of the challenges presented by implementation and design complexities.
  These flexible facets include:
    Categorical indicators – capture diverse inputs and outputs
    Intermediate outcome level – accounts for an underlying theory of influencing causality through an adoption logic
    Outcome-level that looks to measure effective implementation of programme outputs by stakeholders provides a measure of systemic change without requiring onerous methodologies.
  The objective across an entire monitoring system such as this is ultimately to reduce the uncertainty around a programme’s contribution to its objectives while providing a basis for it to adapt to complex and emergent environments in its efforts to influence lasting and systemic change.

## Slide 22
  info@nautilusconsulting.org